## Slide 1
BALKANEA MOBILE — SANDBOX / TEST READINESS
What's needed to connect
the full app to sandbox / test
Open items across authentication, booking, and payments — prepared for
review with Dragana & Hristijan
Stage: TestFlight (v1.0.7, build 11) Systems: RateHawk · Bank checkout · Supabase auth Prepared: August 2026

## Slide 2
01 — AUTHENTICATION
Google, Apple, phone sign-in — what's needed
Sign-in itself is built; what's open is whether the providers are actually switched on, and one App Store requirement.
BALKANEA MOBILE — SANDBOX / TEST READINESS
2
Open
Google & Apple OAuth provider setup
App code is fully built — email/password, phone OTP, Google, Apple, and guest mode all exist today. Unverified: whether Supabase Auth actually has live Google/Apple client credentials configured, and the balkanea://auth/callback redirect allow-listed.
Open
Native “Sign in with Apple”
Only the browser-based Apple OAuth flow exists today. Apple guideline 4.8 generally requires a native Sign-in-with-Apple option whenever other third-party social logins (Google) are offered
Open
Google Play Developer account
Confirmed on the July 24 call: doesn't exist yet. Needed well ahead of any Android submission, since account verification itself takes calendar time independent of app readiness.

## Slide 3
02 — SEARCH & BOOKING
RateHawk sandbox + our own hotel database
The biggest open surface. Search is fully simulated today, and two architecture questions from the last call are still undecided.
BALKANEA MOBILE — SANDBOX / TEST READINESS
3
BLOCKED ON PARTNER
RateHawk sandbox is still trial-only
Need sandbox access end point and credentials
CORRECTION NEEDED
B2C vs. B2B is a pricing/availability split, not a separate hotel file
The master dataset (~4M hotels) is shared between B2C and B2B — the difference is only in price and availability RateHawk exposes per credential type. The mobile app's current code comment describes a separate “B2C-approved hotel file” and needs updating.
Open
Mobile needs its own static hotel database
Confirmed: balkanea.com's WordPress/MySQL database cannot be reused — hotel/room data is mixed into the generic content-page table and is already a known performance problem on web. First concrete step: get the RateHawk master dump (~30GB) onto shared staging and design mobile's own schema.
Open
Search-flow design, and booking endpoints still to build
Undecided: web's live-search-then-enrich pattern vs. DB-first shortcut (query our own DB first, only call RateHawk once a hotel is opened). Either way, the backend has no room-rate, pre-book, or create-order calls yet — results come back with room_types and cancellation_policy null today.

## Slide 4
03 — PAYMENTS
Bank checkout — the WebView approach
Direct in-app payment is a contractual dead end for now; the WebView path reuses what's already approved.
BALKANEA MOBILE — SANDBOX / TEST READINESS
4
IN PROGRESS
Preferred path: WebView to the existing, already-approved checkout page
App creates the order server-side, opens an in-app WebView on the existing web checkout for that order, and the server notifies the app of success/failure. Avoids a new bank agreement and the Apple/Google in-app-purchase commission risk direct-native payment would trigger. Scaffolded in code, not yet wired in.
PENDING FROM PARTNER
Bank plugin documentation
Hristijan has provided documentation but ability to test/credentials still open.
ESTIMATE
A few days of iteration once started
Per Hristijan on the call: building and testing the WebView checkout page properly takes “a few days going back and forth,” not a same-day integration .

## Slide 5
04 — PLANNING
Path to a real sandbox/test build — phased
Claude does all technical implementation; testing and store-asset design draw on existing team time. Two phases are gated by partners, not effort.
BALKANEA MOBILE — SANDBOX / TEST READINESS
5
PHASE 1 - UNBLOCK
Partner-gated, timeline not ours to set
RateHawk sandbox activation to RateHawk), bank agreement clarification for the WebView path, and Google Play Developer account creation (1 day admin + Google's own verification time).
PHASE 2 - BUILD
~2–3 weeks once Phase 1 clears · Claude-implemented
Hotel DB schema + import from RateHawk master dump, room-rate/pre-book/create-order endpoints, payment WebView wired to the real flow, native Sign-in-with-Apple, OAuth provider verification.
PHASE 3 - TEST
~3–5 days, parallel across existing testers
Structured QA across auth, search, booking, and payment — spread across the TestFlight testers. Store assets (screenshots, listing copy): ~2–3 days of design time on top of already-speced UI.
PHASE 4 - SUBMIT
~1 month, both stores · estimate
Apple review ~3–5 days (real travel payments = higher scrutiny). Google Play's 14-day mandatory closed-testing period is the long pole. Budget at least one rejection-and-resubmit round on each store.

## Slide 6
05 — COST
What implementation actually costs
Claude performs all engineering — the cost driver is calendar time and a small set of fixed fees, not dev-team hours.
BALKANEA MOBILE — SANDBOX / TEST READINESS
6
Near-zero marginal cost
Engineering/AI labor
Estimated $400 AI Cost
Existing-team time · rate TBD
Testing & design
QA pass draws on TestFlight testers. Store-asset design (screenshots, listing copy) is a small, scoped task on top of UI that's already built and speced
$124 one-time / ongoing, both platforms
Store & account fees
Apple Developer Program: $99/year (already paid — account approved). Google Play Developer account: $25 one-time. No other store-side fees until real transactions flow through the app.
Partner approvals
What's NOT a dollar cost here
RateHawk sandbox activation and the bank agreement are contractual/relationship items, not engineering spend — their cost is delay risk against the end-of-August/early-September target, not a line item.

## Slide 7
05 — COST
Running cost vs. margin — 10 vs. 100 bookings/day
3% chat-to-booking conversion, 3% RateHawk margin (Luke, July 21), €800 avg. booking value (illustrative — tbc). Same per-session cost baseline as the architecture deck ($0.08/session, Sonnet).
BALKANEA MOBILE — SANDBOX / TEST READINESS
7
10 bookings/day
Bookings / month
300
Nea sessions / month
10,000
Running cost / month
$935
Gross margin revenue / month
~$7,776
Net margin after running cost
~$6,841
Running cost = ~12% of margin revenue
100 bookings/day
Bookings / month
3,000
Nea sessions / month
100,000
Running cost / month
$8,472
Gross margin revenue / month
~$77,760
Net margin after running cost
~$69,288
Running cost = ~11% of margin revenue
Same story at both scales — compute/infrastructure is a small, roughly flat share of margin (~11–12%). Confirms Luke's own read from July 21: marketing/adoption is the real bottleneck, not running cost. On Haiku 4.5 instead of Sonnet, running cost drops to ~$435/mo (10's) and ~$3,472/mo (100's) — further shrinking that share, at a quality trade-off worth testing before committing.

## Slide 8
06 — FOR FRIDAY
What we need decided or moving this week
Plus one hard scheduling constraint that should anchor any target date.
BALKANEA MOBILE — SANDBOX / TEST READINESS
8
RateHawk sandbox
Real status of the activation is progressing — timeline, or next follow-up step.
Search-flow design
Pick one: web's live-search-then-enrich pattern, or the DB-first shortcut — needed before backend work continues.
Payment path
Confirm the WebView-to-existing-checkout approach genuinely avoids a new bank agreement.
Two deliverables to unblock this week
RateHawk master dump onto shared staging and sandbox access, and the bank plugin docs from Ivan.
Store submission, once ready: no Google Play account yet · Apple review ~3–5 days · Google's 14-day closed-testing minimum · ~1 month total per Hristijan's estimate.