## Slide 1
BALKANEA MOBILE — SANDBOX / TEST READINESS UPDATE
Cost, risk, and the path to submission
RateHawk sandbox booking and payments are verified live end-to-end, now with real pricing in the traveler's currency across all three priced regions (LA/Paris/Dubai). See Risks for what's still open. Cost model updated, certification and store submission plan attached.
Stage: TestFlight (v1.0.7, build 11) Systems: RateHawk (sandbox, cert pending) · Bank checkout (MKD, live) · Supabase auth Prepared: August 2026 (update)

## Slide 2
01 — AUTHENTICATION
Google sign-in is live; Apple is the remaining gap
Google OAuth is confirmed working end to end. What's left is Apple's provider secret and the Google Play account.
BALKANEA MOBILE — SANDBOX / TEST READINESS
2
RESOLVED
Google OAuth is live
Confirmed via the Supabase Management API: real client credentials are configured and the balkanea://auth/callback redirect is already allow-listed. No action needed.
BLOCKED
Native Sign-in with Apple — built, not switched on
Native code shipped 8/5, but Supabase's Apple provider has no client secret yet — it'll fail at runtime until that's set. Needs a Services ID + signed JWT from Ray's own Apple Developer account; Claude can't do this part.
Open
Google Play Developer account
Confirmed on the July 24 call: doesn't exist yet. Needed well ahead of any Android submission, since account verification itself takes calendar time independent of app readiness.

## Slide 3
02 — SEARCH & BOOKING
RateHawk sandbox is live; full booking flow proven end-to-end
Sandbox key 973 replaced the blocked key 954 and returns real search results across all sandbox regions. The complete booking sequence -- search, prebook, create order, finish -- has been proven against RateHawk's own certification test hotels, including every mandatory certification scenario.
BALKANEA MOBILE — SANDBOX / TEST READINESS
3
RESOLVED
Sandbox key 973 -- issued and verified 8/24, replacing blocked key 954
RateHawk confirmed the 401s on key 954 were a technical issue on their side, not IP whitelisting -- a new key (973) was issued and verified with real search results. Sandbox itself needs no IP whitelisting at all; that only applies at production certification (see Risks).
CONFIRMED
B2C vs. B2B is a pricing/availability split, not a separate hotel file
The master dataset (~4M hotels) is shared between B2C and B2B — RateHawk exposes only price/availability differently per credential type. The mobile app's code comment describing a separate 'B2C-approved hotel file' still needs a one-line update.
RESOLVED
Mobile's own hotel database is live
850,218 hotels / 3,930,128 rooms imported and indexed across all 10 target countries (0 parse errors). Region-filtered, sorted queries benchmarked at ~0.2ms server-side. Hristijan already has Developer access to query it directly.
CONFIRMED
Full booking flow proven end-to-end in sandbox, including multi-room
Search → prebook → create order → finish now runs successfully against RateHawk's certification test hotels (Conrad LA, Rosa Bell Motel) -- all 7 mandatory scenarios passed, real order IDs captured. Now fully real-priced (search and room selection) across all 3 regions, in the traveler's real currency.

## Slide 4
03 — PAYMENTS
Bank checkout works end-to-end -- confirmed live with NLB, in MKD
Confirmed 8/20 (demo hotel) and 8/25 (real RateHawk hotel, after fixing a merchantTransactionId length bug): real test-card payments clear through NLB via Bankart, from the app's booking flow to a synced Salesforce lead. Settles in MKD -- see Risks for what's still open.
BALKANEA MOBILE — SANDBOX / TEST READINESS
4
SUPERSEDED
WooCommerce bridge — built, verified, ruled out
Hristijan built and documented the ‘Mobile Payment Bridge’ plugin — WebView opens a guest WooCommerce order-pay page, status polled via REST. Verified live against a real staging order. But it's built entirely on WooCommerce's order-key model, which ‘no WooCommerce in the architecture’ now rules out.
CONFIRMED LIVE
Balkanea Payment Bridge -- built and confirmed working end-to-end, MKD settlement
Hristijan's ‘Balkanea Payment Bridge’ plugin (signed HMAC links, Bankart Gateway V3 hosted card form, async Notify webhook) is live. Confirmed 8/20 and re-confirmed 8/25 against a real RateHawk hotel, settling in MKD (Bankart's only supported currency). 8/25 also found and fixed the root cause of intermittent failures -- Hristijan's plugin was silently exceeding Bankart's 50-character reference limit on real-hotel bookings. Fixed app-side; charges now clear reliably.
ACTION THIS WEEK
Outstanding: mobile-responsive card page
Bankart's hosted card page still isn't mobile-responsive, and also doesn't collect billing address or a separate ‘name on card’ field (needed since the payer isn't always the guest). A full written spec -- Balkanea's brand colors, autofill support, and these missing fields -- was sent to Hristijan 8/25. Still his to build.

## Slide 5
04 — PROXY: Proposal VS AWS
proxy proposal vs. what’s built on AWS
Scoped to the static-IP RateHawk requires for PRODUCTION certification -- sandbox itself needs no whitelisting (confirmed 8/24). Both columns are real options.
BALKANEA MOBILE — SANDBOX / TEST READINESS
5
PROXY PROPOSAL
OUR AWS BUILD (LIVE TODAY)
COST
Not costed in his doc. As specified — VPS + Redis + eventual HA instance — realistically ~$20–50+/mo, plus unspecified engineering time to build it.
~$5–8/mo (single small instance), $0 static IP, $0 TLS. Real, verified spend — not an estimate. Redis rate-limiting, BullMQ queueing and HA (standby instance + auto-failover) +$14/month
PERFORMANCE
Designed for high scale from day one (Redis rate-limiting, BullMQ queueing). Higher ceiling, but unbuilt and untested.
Single lightweight instance with HA handles this thin forwarding workload with large headroom. RateHawk’s own rate limits are the real ceiling either way.
STABILITY
Phase 1 as specified is also single-instance . HA to a future phase. Same posture as AWS.
Single instance with standby instance, auto-restart on crash, fully rebuildable from source-controlled scripts. Box itself verified working; RateHawk-specific logic not yet built on either side. HA (standby instance + auto-failover
SUPPORT
No hosting provider or support commitment specified.
Real AWS infrastructure (~99.99% published EC2 SLA). can add paid AWS support later if ever needed.
SCALABILITY
Redis/BullMQ/HA
Redis/BullMQ/HA

## Slide 6
05 — ALIGNMENT & RECOMMENDATION
Same pattern as Analytics — the fastest path to go-live
Both options are real. Here is the case for each, and why one fits this specific requirement better.
BALKANEA MOBILE — SANDBOX / TEST READINESS
6
Aligned with the Analytics Architecture, not a one-off
The same static-IP relay pattern — a small, dedicated, isolated instance with a static IP — is already the documented pattern for Alana Analytics' own extraction relay. Both now live under one AWS Organization, in separate accounts for compliance isolation, following the same internal playbook. Ivan's proposal has no relationship to this existing, already-proven pattern.
MARRA-WIDE
Recommendation: use the AWS build to reach go-live
For the actual requirement -- a static IP RateHawk's production certification will accept -- the AWS build is live, verified, and ~$5–8/mo today, with no further engineering needed. Ivan's fuller proposal suits a mature, high-traffic system, but adopting it as specified means more cost and an unresolved question of who runs it -- neither of which certification itself requires. Fastest path: use what's already built and verified.
RECOMMENDED
63.185.27.197 - Elastic IP attached to the AWS proxy box in eu-central-1 (Frankfurt)

## Slide 7
06 — LIVE DEMO
End-to-end payment now works — from the app
Confirmed 8/20: a real test card cleared through NLB, from the mobile app's own booking flow to a synced Salesforce lead.
BALKANEA MOBILE — SANDBOX / TEST READINESS
7
What happened
A real booking in the app → signed Bankart payment link → Bankart's hosted card form → NLB processing with 3DS → async Notify webhook confirms the booking → Salesforce lead synced. The actual app flow, start to finish — not a browser demo.
LIVE
What it proves: the full stack is real
This wasn't a sandboxed demo — a real card ran through NLB via Bankart, initiated from the actual mobile app, ending in a confirmed booking and a synced CRM lead. Every layer (signed link, hosted card form, async webhook, Supabase state) is now proven live together, not just individually tested.
CONFIRMED
What's still open: the card page isn't mobile-responsive
Bankart's hosted card page (Hristijan's side, outside our control) has alignment issues on phone and tablet screens — the one open item before this is a clean guest-facing checkout on iOS and Android.
OPEN ITEM

## Slide 8
07 — PLANNING
Certification, build, test, submit -- phased
Claude does all technical implementation; testing and store-asset design draw on existing team time. RateHawk's certification review and the app store review clocks are the two timelines genuinely outside our control.
BALKANEA MOBILE — SANDBOX / TEST READINESS
8
PHASE 1 - CERTIFY
Ours to finish, RateHawk's to review
Answer RateHawk's Pre-Certification Checklist in full (payment type, RPM limits, static-data sync, price-parsing field, booking-success signal, full error-handling matrix), submit the AWS static IP for whitelisting, and hand back the real order IDs from the 7 passed test scenarios. RateHawk's own review time after that isn't ours to set.
PHASE 2 - BUILD
~2–3 weeks · Claude-implemented
Replace lib/ratehawk.ts's simulated stub with the real prebook → charge → finish sequence, reconciling that RateHawk charges Balkanea's deposit balance while Bankart charges the guest's card. Build the room-by-room guest configurator that search and booking currently lack entirely (multi-file, not small). Apple's OAuth secret + Google Play account (Ray-owned) proceed in parallel.
PHASE 3 - TEST
~1–2 weeks, parallel across existing testers
Auth, search, and single-room booking + payment are already TestFlight-tested. New coverage once Phase 2 lands: multi-room booking end-to-end, RateHawk's full error-handling matrix (booking_form_expired, rate_not_found, soldout, book_limit, 3ds -- not just the happy path), and a repeat real-money payment run to confirm settlement is clean before certification submission. Store assets (screenshots, listing copy) in parallel -- ~2–3 days on top of already-built UI.
PHASE 4 - SUBMIT
~1 month+, three review clocks running in parallel
Apple review ~3–5 days (real travel payments = higher scrutiny; budget one rejection-and-resubmit round). Google Play's 14-day mandatory closed-testing period is the long pole, and its clock can't start until the Play Developer account exists. RateHawk moves sandbox → production keys only after certification sign-off, on its own timeline, running alongside store review rather than before it.

## Slide 9
08 — ARCHITECTURE
Planned production architecture
Payments and RateHawk booking are now verified live, not just treated as such (see Risks for what's still open); the admin portal's WooCommerce-parity gap is the one box still genuinely open below.
BALKANEA MOBILE — SANDBOX / TEST READINESS
9
CLIENT
BACKEND
DATA
PARTNERS
Balkanea Mobile App
Expo / React Native — iOS, Android, Web. Nea AI (Claude Haiku) search advisor. Booking flow: search → lock → pay → confirm.
Supabase Auth
Google (live) · Apple (native code shipped, provider secret pending) · Phone OTP · Guest.
balkanea-lead-webhook
Vercel serverless (Node.js). Hotel search proxy (real amenity filtering, real multi-currency), RateHawk mobile workflow (SERP / Prebook / create-order), payment gateway, Salesforce sync. CORS gap found and fixed today -- every endpoint had none, silently breaking the whole flow on the web build.
balkanea_hotels_sbx
850,218 hotels / 3.9M rooms, all 10 countries. Plus a sibling sandbox schema (same instance): 742 hotels across the 3 regions RateHawk's own sandbox dump actually prices -- real search and room rates, not simulated, as of today.
LIVE
balkanea_sbx
Bookings, profiles, payment_reference/payment_state (MKD), ratehawk_order_id. Live -- three real bookings written today. New: voucher/invoice PDF fetch + automated confirmation emails via Resend.
RateHawk
Separate mobile Office (contract “balkanea-mobile”). Sandbox key 973 live and verified -- booking mechanics proven end-to-end against certification test hotels. Certification checklist submission is next, then production key.
IN PROGRESS
Payment gateway (NLB-direct)
Confirmed 8/20: real end-to-end card payment cleared through NLB via Bankart's hosted card form, from the app's own booking flow, settling in MKD. Refunds still unbuilt.
LIVE
Salesforce CRM
Leads, booking sync, agent escalation.
client SDK
Admin Portal
admin-payments.html — bookings + payment state, Capture/Void stubbed. Doesn’t cover WooCommerce’s refunds/cancellations/invoicing yet — inventorying that gap for Monday.
PARTIAL
AWS Relay (static IP)
AWS box in eu-central-1 (Frankfurt) -- static Elastic IP (63.185.27.197), live and verified. Required for RateHawk's production certification; sandbox itself needs no whitelisting.
LIVE

## Slide 10
09 — COST
What implementation actually costs
Claude performs all engineering — the cost drivers are calendar time, a small set of fixed fees, and the hotel-DB’s own hosting bill.
BALKANEA MOBILE — SANDBOX / TEST READINESS
10
Near-zero marginal cost
Engineering/AI labor
Estimated $1,000 engineering cost (Claude Code, near-zero if on subscription) -- reflects 8/25's payment debugging, reliability fixes, and new document/email features.
Existing-team time · rate TBD
Testing & design
QA pass draws on TestFlight testers. Store-asset design (screenshots, listing copy) is a small, scoped task on top of UI that's already built and speced
$124 one-time / ongoing, both platforms
Store & account fees
Apple Developer Program: $99/yr (already paid, approved). Google Play: $25 one-time. No other store-side fees until real transactions flow.
Partner approvals
What's NOT a dollar cost here
RateHawk sandbox activation and the payment-architecture decision are relationship items, not engineering spend — the cost is delay risk against the Aug/Sept target, not a line item.
LIVE — SCALES WITH USAGE
Hotel database hosting (Supabase)
Sandbox ~$25/mo, production ~$75/mo (Supabase Pro). Plus the AWS relay for RateHawk certification: ~$8/mo base, ~$22/mo with HA -- in the updated cost model.

## Slide 11
10 — WHAT’S BEEN BUILT
Full scope, real codebase size, and what it would have cost elsewhere
Every feature below is built and verified, not planned. Right: an illustrative traditional-agency cost for the same scope — not a real quote, for contrast only.
BALKANEA MOBILE — SANDBOX / TEST READINESS
11
SCOPE BUILT
• Cross-platform app shell (iOS / Android / Web) + AI concierge (Nea)
• 850K-hotel content DB + real RateHawk-priced sandbox DB (3 regions), real amenity filtering
• Real RateHawk booking flow — search / prebook / finish / status, all 7 certification scenarios, multi-room (real per-room guest configurator, not the flat-integer gap flagged earlier)
• Real Bankart/NLB payment integration (correct multi-currency: EUR/USD direct from RateHawk, MKD via peg conversion) + voucher/invoice PDF retrieval
• Auth: Google OAuth, native Apple Sign-In, guest checkout
• Salesforce CRM sync, admin portal
• Automatic booking emails — guest confirmation + business notification, each with a RateHawk PDF attached (voucher / invoice), shipped today via Resend
• Push notifications
• Voice AI (LiveKit/Retell) — built and working, shelved for a leaner V1
Languages: 2 — English + Macedonian (Cyrillic), the actual translated UI.
Currencies: 9, across 11 countries. For the 3 real-priced regions, EUR/USD come directly from RateHawk (real FX); MKD converts from that real quote via a fixed peg rate.
ACTUAL CODEBASE, ~10 WEEKS ELAPSED (first commit 6/18 → 8/26)
Mobile: 17 screens · 12 components · 27 lib modules · ~14,700 lines TS/TSX · 7 migrations · 92 commits
Backend: 12 endpoints · 12 lib modules · ~4,500 lines JS · 78 commits
IF BUILT BY A TRADITIONAL AGENCY (ILLUSTRATIVE, NOT A REAL QUOTE)
Component | Blended $100–180/hr
Discovery & UX | $15–25K
App shell / design system | $10–15K
Auth | $8–12K
Hotel search / content DB | $20–30K
AI concierge chat | $25–40K
Real booking flow (RateHawk) | $35–55K
Payment integration (Bankart) | $25–40K
Admin portal | $8–12K
Salesforce CRM | $8–12K
i18n | $8–12K
Voice AI (shelved) | $15–25K
QA across iOS/Android/Web | $15–25K
Subtotal ~$192K–303K, +15–20% PM/coordination → ~$220K–360K all-in.
Typically 4–7+ months with a small team. Nearshore/offshore: ~40–50% of that (~$110K–180K), usually a longer timeline.
This build: ~10 weeks, ~$1,000 estimated engineering cost (see Cost slide).

## Slide 12
11 — COST
Running cost vs. margin — 10 vs. 100 bookings/day
3% chat-to-booking conversion, 3% RateHawk margin (Luke, July 21), €800 avg. booking value (illustrative — tbc). Same per-session cost baseline as the architecture deck ($0.08/session, Sonnet).
BALKANEA MOBILE — SANDBOX / TEST READINESS
12
10 bookings/day
Bookings / month
300
Nea sessions / month
10,000
Running cost / month
$1,018
Gross margin revenue / month
~$7,776
Net margin after running cost
~$6,759
Running cost = ~13% of margin revenue
100 bookings/day
Bookings / month
3,000
Nea sessions / month
100,000
Running cost / month
$8,555
Gross margin revenue / month
~$77,760
Net margin after running cost
~$69,205
Running cost = ~11% of margin revenue
Same story at both scales -- compute/infrastructure (now including the AWS static-IP relay required for RateHawk certification) is a small, roughly flat share of margin (~11–13%). Confirms Luke's own read from July 21: marketing/adoption is the real bottleneck, not running cost. On Haiku 4.5 instead of Sonnet, running cost drops to ~$518/mo (10's) and ~$3,555/mo (100's) -- further shrinking that share, at a quality trade-off worth testing before committing.

## Slide 13
12 — PERFORMANCE & SCALE
The real technical ceiling on today's stack, measured live
RateHawk sandbox rate limits measured directly against the live API today. These are SANDBOX limits, not confirmed production ones -- see the note below before treating the ceiling as fixed.
BALKANEA MOBILE — SANDBOX / TEST READINESS
13
search/serp/hotels/
150 / min
Search results list -- ONE call prices a whole region (~250 hotels), not one call per hotel.
HEADROOM
hotel/prebook/
30 / min
Room lock, right before payment. Comfortable headroom above the booking-flow bottleneck.
HEADROOM
search/hp/
10 / min
Single-hotel room rates -- required on room selection AND before every booking. This is the binding constraint.
BOTTLENECK
10/min on search/hp/ → 600/hour → ~14,400/day ceiling on real room-rate views, and therefore on bookings, under today's sandbox limits.
This is a technical ceiling, not a target or a forecast — real booking volume will be governed by guest demand, far below any of these limits.
Database: comfortable headroom
Supabase Postgres allows 120 concurrent connections; each Vercel function instance currently pools at most 3. Not a near-term constraint at any traffic level discussed here.
NOT A CONSTRAINT
Infra tier: Vercel Hobby plan
Fine for the current testing phase -- no verified request/day figure exists for it, so none is claimed here. Real pre-launch item: Hobby has no SLA and stricter usage limits than Pro; upgrade before real production traffic.
PRE-LAUNCH ITEM

## Slide 14
13 — RISKS
What's still open, now that payments and RateHawk are live
Multi-room booking, real-hotel payments, and RateHawk’s live wiring -- all previously flagged here -- are now built, fixed, and verified as of 8/25. These are the risks that remain.
BALKANEA MOBILE — SANDBOX / TEST READINESS
14
RateHawk's sandbox documents (voucher + invoice) return a blank placeholder, not real content
Fetching both via RateHawk's real document endpoints returns byte-for-byte identical PDFs -- embedded metadata reads 'Acrobat Distiller 6.0 (Windows)', dated 2006-03-06, clearly a generic template, not a generated document. Not a bug in our integration (request/response plumbing verified correct) -- needs re-verification once production RateHawk credentials are active; sandbox may simply have no real content to render.
SANDBOX LIMITATION
A reliability bug caused three duplicate real charges today, before being fixed
The booking screen could get stuck indefinitely on ‘Confirming with the hotel’ if a step failed after payment had already captured. Because real RateHawk confirmation genuinely takes 90-140+ seconds, this read as frozen; force-quitting and retrying created a brand-new charge each time. Result: three real Bankart charges for one intended test booking -- harmless only because it was a test card. Now fixed (proper error states + a real progress bar); the lesson is this exact bug class is what causes real duplicate charges against a real guest.
FIXED TODAY
Bankart's hosted card page still isn't mobile-responsive
Input fields still misalign on phone and tablet, and the page has no billing-address or independent 'name on card' field (a guest can pay for someone else's booking). A full written spec -- brand colors, autofill attributes, missing fields -- was sent to Hristijan 8/25. Not yet built on his side.
OPEN — HRISTIJAN
Business-team booking notification email is hardcoded to a placeholder address
New today: confirmed real RateHawk bookings now trigger automated emails -- the guest gets their voucher PDF, the business team gets the invoice PDF (Resend). The business recipient is currently hardcoded to Ray's own address as a placeholder, not a real shared team inbox -- needs to move before this is production-ready.
PLACEHOLDER

## Slide 15
14 — STILL OPEN
What's still genuinely open, and who owns it
The strategic risks are on the Risks slide. This is the operational punch list.
BALKANEA MOBILE — SANDBOX / TEST READINESS
15
Apple + Google Play accounts
Apple: native Sign-in code shipped 8/5, still needs a Services ID + signed JWT from Ray's own Apple Developer account. Google Play: developer account still not created (confirmed not started as of the July 24 call) -- account verification itself takes calendar time independent of app readiness. Both Ray-owned, not build-gated.
Bankart mobile-responsive checkout
Bankart's hosted card page isn't mobile-responsive today, and is missing billing-address and cardholder-name fields. Written spec sent to Hristijan 8/25 (design tokens, autofill attributes, field list). On his side to build.
Admin portal WooCommerce-parity gap
admin-payments.html covers bookings + payment state, with Capture/Void stubbed -- but doesn't yet cover WooCommerce's refunds/cancellations/invoicing. Gap inventoried, not yet built.
deliverables to unblock this week
From Ray: Apple Services ID/JWT, Google Play account. From Hristijan: mobile-responsive fix + billing/cardholder-name fields (spec sent 8/25). From Claude: RateHawk wiring + multi-room build are both done -- next is RateHawk's certification questionnaire.
Store submission, once ready: no Google Play account yet · Apple review ~3–5 days · Google's 14-day closed-testing minimum · RateHawk cert runs in parallel.